## Product_Backlog
Epic | User Story | Description | Priority | Acceptance Criteria | Sprints
Project Initiation and Planning | Conduct Stakeholder Meetings | As a project manager, I want to conduct stakeholder meetings to align on project goals. | High | Meeting minutes documented and approved by all stakeholders. | 1
| Define Project Vision and Objectives | As a project team, we need to define the project vision and objectives to guide the project. | High | Documented vision and objectives reviewed and approved. | 1
| Identify Key Requirements | As a business analyst, I need to gather and document requirements from stakeholders. | High | Complete requirements document approved by stakeholders. | 1
Market Research and Analysis | Perform Market Research | As a project analyst, I need to perform market research and competitor analysis. | High | Market research report compiled and reviewed by the team. | 2
2
2
2
2
2
Factory Design and Setup | Design Factory Floor Layout | As an engineer, I need to design the factory floor layout for optimal efficiency. | Medium | Floor layout design reviewed and approved by the team. | 3
| Plan Utilities | As a utilities planner, I need to plan the layout for electricity, water, and ventilation. | Medium | Utility layout plans approved by engineers and utility providers. | 3
| Select and Source CNC Machines | As a procurement specialist, I need to select and source CNC machines and equipment. | Medium | List of selected machines and equipment, with supplier contracts. | 3
| Develop Workflow Diagrams | As a production planner, I need to develop workflow diagrams for the production process. | Medium | Workflow diagrams reviewed and approved by the team. | 3
3
Infrastructure and Equipment Setup | Construct Factory Building | As a construction manager, I need to oversee the construction of the factory building. | High | Factory building constructed according to plans, within budget. | 4
| Install Electrical and Plumbing | As a contractor, I need to install electrical and plumbing systems in the factory. | High | Electrical and plumbing systems installed and tested. | 4
| Set Up Ventilation and Climate Control | As an HVAC specialist, I need to set up ventilation and climate control systems. | High | Ventilation systems installed and functioning. | 4
4
4
CNC Machine Procurement and Integration | Identify and Select CNC Machines | As a procurement manager, I need to identify, select, and procure CNC machines. | Medium | CNC machines delivered to the factory. | 5
| Procure CNC Machines and Other Equipment | As a procurement manager, I need to procure CNC machines and other equipment. | Medium | Procurement orders placed and equipment received. | 5
| Install and Test CNC Machines | As a technician, I need to install and test the CNC machines. | Medium | CNC machines installed, tested, and calibrated. | 5
5
5
5
5
5
5
5
5
IT Infrastructure and Software Integration | Design IT Network Architecture | As an IT specialist, I need to design the IT network architecture. | Medium | IT network design plan approved. | 6
| Install and Configure Control Software | As a software engineer, I need to install and configure control software for CNC machines. | Medium | Control software installed and configured. | 6
| Implement Production Management Software | As an operations manager, I need to implement production management software. | Medium | Production management software installed and staff trained. | 6
6
6
6
6
6
6
6
6
6
6
Staff Hiring and Training | Hire Skilled Personnel | As an HR manager, I need to hire skilled personnel (operators, engineers, maintenance staff) | High | Staff hired and onboarded. | 7
| Develop and Implement Training Programs | As a training manager, I need to develop and implement training programs. | High | Training programs conducted and staff certified. | 7
| Conduct Safety Training and Certification | As a safety officer, I need to conduct safety training and certification for all staff. | High | All staff certified in safety training. | 7
Quality Assurance and Production Launch | Develop Quality Assurance Processes | As a quality assurance manager, I need to develop QA processes and protocols. | Medium | QA processes documented and staff trained. | 8
| Conduct Trial Runs and Performance Testing | As a production manager, I need to conduct trial runs and performance testing. | Medium | Successful trial runs with documented performance data. | 8
| Implement Quality Control Measures | As a QC manager, I need to implement quality control measures for production. | Medium | QC measures implemented and regularly reviewed. | 8
| Begin Phased Production Launch | As an operations manager, I need to begin phased production launch. | High | Phased production launch completed. | 8
| Monitor Initial Production | As a production supervisor, I need to monitor initial production closely and gather feedback. | High | Production data collected and feedback documented. | 8
| Implement Continuous Improvement | As a continuous improvement manager, I need to adjust and refine processes based on feedback. | High | Continuous improvement practices implemented. | 8

## for calculation
Role | Salaries per Year
Production Engineers | 700000
Mechanical Engineers | 800000
Quality Assurance Specialists | 700000
Production Managers | 1000000
Business Analyst | 800000
Procurement Specialist | 600000
Safety Officer | 600000
Construction manager | 1050000
IT specialist | 870000
Software Engineer | 600000
Network Engineer | 380000
Training Manager | 587000
Stakeholders | 1200000
Project Manager | 900000
Structural Engineer | 900000
Utilities Provider | 500000
Plumber | 300000
Electricians | 400000
HVAC Technicians | 500000
Construction Workers | 250000
Technician Team | 800000
Operations Manager | 550000
System Administrator | 360000
HR Manager | 350000
Machine Operators | 350000
Operators | 350000

## sprint1
Sprint 1 Weeks(1-2) |  |  | BUDGET ALLOCATED | 120000
Sprint Goal : Project Initiation
Task | Description | Assignee | Status | Priority | Start Date | End Date | Story Points | Comments
Conduct Stakeholder Meetings | Align on project goals and expectations | Business Analyst | completed | High | 2024-01-01 | 2024-01-06 | 2 | Schedule and organize initial meetings
Define Project Vision | Create project vision and outline objectives | Procurement Specialist | completed | High | 2024-01-01 | 2024-01-14 | 2 | Align with stakeholders on project goals
Identify Key Requirements | Gather initial requirements from stakeholders | Business Analyst | completed | High | 2024-01-01 | 2024-01-14 | 3 | Collect and document initial requirements
Estimated Number of Professionals Involved
ROLE | ESTIMATED INVOLVEMENT | NO. OF PERSON INVOLVE IN THE ROLE
BUSINESS ANALYST | FULL TIME | 1
STAKEHOLDERS | PART TIME (20%) | 3
PROJECT MANAGER | FULL TIME | 1

## sprint2
Sprint 2 (Week 3-4) |  |  | BUDGET ALLOCATED | 195000
Sprint Goal- Requirement Analysis
Task | Description | Assignee | Status | Priority | Start Date | End Date | Story Points | Comments
Gather and Document Requirements | Conduct detailed requirement analysis | Business Analyst | completed | High | 2024-01-15 | 2024-01-28 | 5 | Document and obtain approval from stakeholders
Negotiate Contracts | Negotiate with vendors to secure the best prices and terms for any outsourced services or products. | Procurement Specialist | completed | Medium | 2024-01-16 | 2024-01-20 | 3 | Focus on getting the best deals within budget.
Source Tools and Software | Identify and procure any required tools or software needed for market research, documentation, or data analysis. | Procurement Specialist | completed | Medium | 2024-01-21 | 2024-01-28 | 3 | Ensure all necessary tools are sourced efficiently.
Review Requirement Documentation | Examine the gathered requirements to ensure they are complete, clear, and free of ambiguities. | Quality Assurance Specialists | completed | High | 2024-01-15 | 2024-01-18 | 2 | Provide feedback and suggest improvements if necessary.
Validate Market Research Report | Ensure that the market research and competitor analysis are conducted thoroughly and that the findings are accurate and reliable. | Quality Assurance Specialists | completed | High | 2024-01-15 | 2024-01-28 | 3 | Review and validate the report for accuracy.
Perform Market Research | Analyze market trends and competitors | Business Analyst | completed | High | 2024-01-20 | 2024-01-28 | 5 | Compile and review market research report
Estimated Number of Professionals Involved & their SALARIES | [8 empty] | SALARY | (Multiple Items)
ROLE | ESTIMATED INVOLVEMENT | NO. OF PERSON INVOLVE IN THE ROLE | SALARY PER YEAR | SALARY |  |  |  |  | Row Labels | Sum of SALARY
Business Analyst | FULL TIME | 1 | 800000 | 66666.6667 |  |  |  |  | Business Analyst | 66666.6667
STAKEHOLDERS | PART TIME (20%) | 3 | 1200000 | 60000 |  |  |  |  | PROCUREMENT SPECIALIST | 50000
PROCUREMENT SPECIALIST | FULL TIME | 1 | 600000 | 50000 |  |  |  |  | Project Manager | 75000
Quality Assurance Specialists | FULL TIME | 1 | 700000 | 58333.3333 |  |  |  |  | Quality Assurance Specialists | 58333.3333
Project Manager | FULL TIME | 1 | 900000 | 75000 |  |  |  |  | STAKEHOLDERS | 100000
|  |  | TOTAL SALARIES | 310000 |  |  |  |  | Grand Total | 350000
BUDGET ALLOCATED (Sprint1 + sprint2) | MONEY SPEND (SALARIES + MISCELLANEOUS) | OBSERVATION
315000 | 315000 | WITHIN ALLOCATED BUDGET

## sprint3
Sprint 3 (Weeks 5-6) |  |  | BUDGET ALLOCATED | 280000
Sprint Goal: Factory Design
Task | Description | Assignee | Status | Priority | Start Date | End Date | Story Points | Comments
Design Factory Floor Layout | Optimize factory floor layout for efficiency | structural engineer,mechanical engineer | Completed | High | 2024-01-29 | 2024-02-06 | 5 | Measure space and create layout design
Plan Utilities | Plan layout for electricity, water, and ventilation | structural engineer,mechanical engineer,utility provider | Completed | Medium | 2024-02-07 | 2024-02-11 | 3 | Coordinate with utility providers
Gather Requirements and Document | Collaborate with stakeholders and development team to ensure all requirements for the factory design are well captured and documented. | Business Analyst | Completed | High | 2024-01-29 | 2024-02-11 | 5 | Ensure alignment between stakeholders and the engineering team regarding the design and utility plans.
Optimize Factory Floor Layout for Efficiency | Work with the engineering team to ensure the factory floor layout is optimized for production efficiency. | Production Manager | Completed | Medium | 2024-01-29 | 2024-02-11 | 3 | Review designs and provide feedback to ensure practicality for production processes.
Ensure Safety Compliance and Risk Assessment | Ensure that all designs and plans comply with relevant safety regulations and standards. | Safety Officer | Completed | High | 2024-01-29 | 2024-02-11 | 5 | Conduct risk assessments and provide safety best practices.
Estimated Number of Professionals Involved
ROLE | ESTIMATED INVOLVEMENT | NO. OF PERSON INVOLVE IN THE ROLE
Structural Engineer | FULL TIME | 2
Mechanical Engineer | FULL TIME | 2
Business Analyst | FULL TIME | 1
Production Engineers | FULL TIME | 1
Safety Officer | FULL TIME | 1
Utilities Provider | FULL TIME | 2

## sprint4
Sprint 4 (Weeks 7-8)
Sprint Goal: Equipment Selection
Task | Description | Assignee | Status | Priority | Start Date | End Date | Story Points | Comments
Select and Source CNC Machines | Identify and order suitable equipment | Procurement Specialist | Completed | Medium | 2024-02-12 | 2024-02-25 | 3 | Evaluate and select best options
Develop Workflow Diagrams | Map out production workflows | Production Engineers | Completed | Medium | 2024-02-14 | 2024-02-25 | 3 | Create and review workflow diagrams
Analyze Business Requirements | Collect and analyze business requirements to determine specifications for CNC machines and production workflows. Coordinate with stakeholders to ensure alignment with business goals. | Business Analyst | Completed | High | 2024-02-12 | 2024-02-25 | 3 | Vital to ensuring that selected machines and workflows meet business objectives.
Provide Technical Expertise on CNC Machines | Assess technical requirements for CNC machines. Provide recommendations on suitable models and ensure compatibility with existing production processes. | Mechanical Engineers | Completed | High | 2024-02-12 | 2024-02-25 | 5 | Crucial for selecting equipment that meets technical and production needs.
Conduct Quality Assurance Review | Develop and implement a quality assurance plan for new equipment and workflows. Conduct inspections and tests to ensure compliance with quality standards. | Quality Assurance Specialists | Completed | High | 2024-02-12 | 2024-02-25 | 5 | Essential for maintaining product quality and meeting industry standards. | SALARY PER YEAR | (Multiple Items)
Estimated Number of Professionals Involved & their SALARIES | [8 empty] | Row Labels | Sum of SALARY
ROLE | ESTIMATED INVOLVEMENT | NO. OF PERSON INVOLVE IN THE ROLE | SALARY PER YEAR | SALARY |  |  |  |  | Business Analyst | 66666.6667
Business Analyst | FULL TIME | 1 | 800000 | 66666.6667 |  |  |  |  | 1 | 66666.6667
Mechanical Engineers | FULL TIME | 1 | 800000 | 66666.6667 |  |  |  |  | Mechanical Engineers | 66666.6667
Production Engineers | FULL TIME | 1 | 700000 | 58333.3333 |  |  |  |  | 1 | 66666.6667
Procurement Specialist | FULL TIME | 1 | 600000 | 50000 |  |  |  |  | Procurement Specialist | 50000
Quality Assurance Specialists | FULL TIME | 1 | 700000 | 58333.3333 |  |  |  |  | 1 | 50000
Structural Engineer | FULL TIME | 1 | 900000 | 75000 |  |  |  |  | Production Engineers | 58333.3333
Safety officer | FULL TIME | 1 | 600000 | 50000 |  |  |  |  | 1 | 58333.3333
|  |  | Total | 425000 |  |  |  |  | Quality Assurance Specialists | 58333.3333
[9 empty] | 1 | 58333.3333
[9 empty] | Safety officer | 50000
[9 empty] | 1 | 50000
[9 empty] | Structural Engineer | 75000
[9 empty] | 1 | 75000
[9 empty] | Grand Total | 425000
BUDGET ALLOCATED | MONEY SPEND (SALARIES + MISCELLANEOUS) | OBSERVATION
430000 | 430000 | WITHIN ALLOCATED BUDGET

## sprint5
Sprint 5 (Weeks 9-10) |  | BUDGET ALLOCATED | 5700000
Sprint Goal: Infrastructure Setup
Task | Description | Assignee | Status | Priority | Start Date | End Date | Story Points | Comments
Manage Construction Contracts | Hire and manage contractors for various construction tasks. Oversee contract execution and ensure timely delivery of services. | Construction Manager | completed | High | 2024-02-27 | 2024-03-11 | 3 | Ensure construction is within budget
Install Plumbing Systems | Install and test electrical and plumbing systems | Plumber | completed | High | 2024-02-28 | 2024-03-11 | 5 | Ensure all plumbing installations are leak-proof and fully operational.
Analyze Business Requirements | Collect and analyze business requirements to ensure infrastructure setup aligns with business goals. Collaborate with stakeholders and developmen team to define specifications. | Business Analyst | completed | High | 2024-02-27 | 2024-03-11 | 3 | Ensure infrastructure setup supports operational efficiency and scalability.
Install Electrical Systems | Install and test electrical wiring and fixtures. Ensure compliance with safety standards and reliable operation of electrical systems. | Electricians | not completed | High | 2024-02-27 | 2024-03-11 | 8 | Ensure all electrical installations are safe and fully operational.
Install HVAC Systems | Install and test heating, ventilation, and air conditioning systems. Ensure systems meet energy efficiency standards and provide optimal climate control. | HVAC Technicians | not completed | High | 2024-02-29 | 2024-03-11 | 5 | Ensure HVAC systems are functioning efficiently and effectively.
Provide Technical Expertise on Infrastructure Design | Assess technical requirements and provide recommendations for infrastructure. Ensure designs meet structural integrity and safety standards. | Civil Engineer | completed | High | 2024-02-27 | 2024-03-11 | 5 | Ensure technical compatibility and efficiency of infrastructure setup.
Execute Construction Tasks | Carry out construction tasks, including foundation, framing, insulation, and interior work. Ensure adherence to safety standards and regulations. | Construction Workers | not completed | High | 2024-02-27 | 2024-03-11 | 8 | Ensure timely completion of construction tasks with high quality.
Oversee Structural Design and Integrity | Design structural elements and oversee their implementation. Ensure compliance with safety standards and regulations. | Structural Engineers | not completed | High | 2024-02-27 | 2024-03-11 | 8 | Ensure the structural integrity of the factory building.
Conduct Safety Inspections | Develop and implement safety protocols. Conduct regular safety inspections to ensure a safe working environment. | Safety Officer | not completed | High | 2024-02-27 | 2024-03-11 | 5 | Ensure compliance with all safety regulations and standards.
Oversee Construction Progress | Manage overall construction progress. Ensure construction stays within budget and timeframe, and complies with all regulations. | Construction Manager | not completed | High | 2024-02-27 | 2024-03-11 | 8 | Ensure smooth execution of construction tasks and timely completion.
Conduct Quality Assurance Reviews | Develop and implement a quality assurance plan for construction. Conduct inspections and tests to ensure compliance with quality standards. | Quality Assurance Manager | not completed | High | 2024-02-27 | 2024-03-11 | 8 | Ensure high quality and durability of construction work.
Construction Material Cost Analysis
Material | Costing
Concrete (Foundation and Structural elements) | 1000000
Steel (Framework and Reinforcements) | 1500000
Insulation (Temperature Control and Energy Efficiency) | 500000
Drywall and Plaster (Interior Walls and Partitions) | 400000
Electrical Wiring and Fixtures | 600000
Plumbing Pipes and Fixtures | 400000
HVAC Systems | 600000
Total | 5000000
Estimated Number of Professionals Involved
ROLE | ESTIMATED INVOLVEMENT | NO. OF PERSON INVOLVE IN THE ROLE
Business Analyst | Full Time | 1
Quality Assurance Manager | Full Time | 1
Construction Manager | Full Time | 1
Plumber | Full Time | 2
Electricians | Full Time | 3
HVAC Technicians | Full Time | 2
Mechanical Engineer | Full Time | 1
Construction Workers | Full Time | 20
Structural Engineers | Full Time | 1
Safety Officer | Full Time | 1
Construction Manager | Full Time | 1
Observation:Sprint planning is partially completed. While construction is finished, the electrical system, HVAC system, and inspection still need to be completed.

## sprint6
Sprint 6 (Weeks 11-12) |  |  |  |  | BUDGET ALLOCATED | 7950000
Sprint Goal: Infrastructure Setup + CNC Machine Procurement(4-CNC Lathe Machine)
Task | Description | Assignee | Status | Priority | Start Date | End Date | Story Points | Comments
Oversee Structural Design and Integrity | Design structural elements and oversee their implementation. Ensure compliance with safety standards and regulations. | Structural Engineer | completed | High | 2024-03-12 | 2024-03-25 | 8 | Ensure the structural integrity of the factory building.
Conduct Safety Inspections | Develop and implement safety protocols. Conduct regular safety inspections to ensure a safe working environment. | Safety Officer | completed | High | 2024-03-12 | 2024-03-25 | 3 | Ensure compliance with all safety regulations and standards.
Install Electrical Systems | Install and test electrical wiring and fixtures. Ensure compliance with safety standards and reliable operation of electrical systems. | Electricians | completed | High | 2024-03-12 | 2024-03-25 | 8 | Ensure all electrical installations are safe and fully operational.
Install HVAC Systems | Install and test heating, ventilation, and air conditioning systems. Ensure systems meet energy efficiency standards and provide optimal climate control. | HVAC Technicians | completed | High | 2024-03-12 | 2024-03-25 | 8 | Ensure HVAC systems are functioning efficiently and effectively.
Conduct Safety Inspections | Develop and implement safety protocols. Conduct regular safety inspections to ensure a safe working environment. | Safety Officer | completed | High | 2024-03-12 | 2024-03-25 | 3 | Ensure compliance with all safety regulations and standards.
Oversee Construction Progress | Manage overall construction progress. Ensure construction stays within budget and timeframe, and complies with all regulations. | Construction manager | completed | High | 2024-03-12 | 2024-03-25 | 5 | Ensure smooth execution of construction tasks and timely completion.
Conduct Quality Assurance Reviews | Develop and implement a quality assurance plan for construction. Conduct inspections and tests to ensure compliance with quality standards. | Quality Assurance Specialists | completed | High | 2024-03-12 | 2024-03-25 | 5 | Ensure high quality and durability of construction work.
Identify and Select CNC Machines | Evaluate and select CNC machines | Procurement Specialist | completed | Medium | 2024-03-12 | 2024-03-14 | 5 | Ensure machines meet production needs
Procure CNC Machines | Place orders and arrange delivery | Procurement Specialist | completed | Medium | 2024-03-15 | 2024-03-25 | 3 | Ensure timely procurement and delivery
Install and Test CNC Machines | Install and calibrate CNC machines | Technician Team | completed | Medium | 2024-03-14 | 2024-03-25 | 8 | Ensure machines are installed and calibrated
Analyze Business Requirements and Financial Viability | Evaluate business needs, financial constraints, and ensure that procurement aligns with business objectives. | Business Analyst | completed | Medium | 2024-03-12 | 2024-03-25 | 5 | Ensure procurement aligns with overall business strategy and budget.
Provide Technical Support and Testing | Assist with technical specifications, ensure mechanical integrity, and support the testing process. | Mechanical Engineers | completed | Medium | 2024-03-12 | 2024-03-25 | 8 | Ensure mechanical components are installed and functioning properly.
Verify Quality Standards | Monitor installation and calibration to ensure that machines meet quality standards and production requirements. | Quality Assurance Specialists | completed | Medium | 2024-03-12 | 2024-03-25 | 5 | Ensure that the procurement and installation process adheres to quality standards.
Estimated Number of Professionals Involved & their SALARIES
ROLE | ESTIMATED INVOLVEMENT | NO. OF PERSON INVOLVE IN THE ROLE | SALARY PER YEAR | SALARY
Electricians | Full Time | 3 | 400000 | 33333.3333
HVAC Technicians | Full Time | 2 | 500000 | 41666.6667
Safety Officer | Full Time | 1 | 600000 | 50000
Construction Manager | Full Time | 1 | 1050000 | 87500
Quality Assurance Specialists | Full Time | 1 | 700000 | 58333.3333
Structural Engineer | Full Time | 1 | 900000 | 75000
Procurement Specialist | Full Time | 1 | 600000 | 50000
Technician Team | Full Time | 2 | 800000 | 66666.6667
Business Analyst | Full Time | 1 | 800000 | 66666.6667
Mechanical Engineers | Full Time | 2 | 800000 | 66666.6667
Production Engineers | Full Time | 2 | 700000 | 58333.3333
Quality Assurance Specialists | Full Time | 1 | 700000 | 58333.3333
Structural Engineer | Full Time | 1 | 900000 | 75000
Safety Officer | Full Time | 1 | 600000 | 50000
|  |  | Total | 837500
Estimated cost of 4-CNC Lathe machine | 7000000
BUDGET ALLOCATED(procurement of cnc machine + salaries) | 7600000
MONEY SPEND | 7000000
REMAINING | 600000 | [7 empty] | Row Labels | Sum of SALARY
[9 empty] | Business Analyst | 66666.6667
[9 empty] | Construction Manager | 87500
[9 empty] | Electricians | 33333.3333
BUDGET ALLOCATED (sprint 5 + sprint 6) | MONEY SPEND (SALARIES + MISCELLANEOUS) | OBSERVATION | [6 empty] | HVAC Technicians | 41666.6667
13650000 | 13650000 | WITHIN ALLOCATED BUDGET | [6 empty] | Mechanical Engineers | 66666.6667
[9 empty] | Procurement Specialist | 50000
[9 empty] | Production Engineers | 58333.3333
[9 empty] | Quality Assurance Specialists | 116666.6667
[9 empty] | Safety Officer | 100000
[9 empty] | Structural Engineer | 150000
[9 empty] | Technician Team | 66666.6667
[9 empty] | Grand Total | 837500

## sprint7
Sprint 7 (Weeks 13-14) |  |  | BUDGET ALLOCATED | 1700000
Sprint Goal: IT Infrastructure and Software Integration
Task | Description | Assignee | Status | Priority | Start Date | End Date | Story Points | Comments
Design IT Network Architecture | Plan and design IT network setup | IT Specialist | Completed | High | 2024-03-26 | 2024-04-08 | 5 | Ensure network design supports factory operations
Install and Configure Control Software for CNC Machines | Set up control software for CNC machines | Software Engineer | Completed | High | 2024-03-26 | 2024-04-08 | 3 | Ensure control software is installed and configured properly
Implement Production Management Software | Train staff on production management software | Operations Manager | Completed | Medium | 2024-03-27 | 2024-04-08 | 3 | Ensure staff is trained on production management software
Design and Configure Network Infrastructure | Design and configure the network infrastructure to support CNC machines and other IT requirements. | Network Engineer | Completed | High | 2024-03-26 | 2024-04-08 | 5 | Ensure the network infrastructure is robust and supports all operations.
Maintain and Troubleshoot IT Systems | Oversee the maintenance and troubleshooting of all IT systems, ensuring they are operating smoothly. | System Administrator | Completed | Medium | 2024-03-27 | 2024-04-08 | 3 | Ensure minimal downtime and address any IT-related issues promptly
Conduct Training Sessions | Conduct training sessions for staff on new software and systems, ensuring they are proficient in their use. | Training Specialist | Completed | High | 2024-03-26 | 2024-04-08 | 2 | Ensure all staff members are confident and capable in using the new systems.
Verify Quality Standards | Monitor the integration process to ensure all software and systems meet quality standards. | Quality Assurance (QA) Manager | Completed | Medium | 2024-03-27 | 2024-04-08 | 3 | Ensure all implementations adhere to quality and performance standards.
Analyze Business Requirements and Ensure Alignment | Evaluate business needs and financial constraints, ensuring that all IT and software implementations align with business objectives. | Business Analyst | Completed | Medium | 2024-03-27 | 2024-04-08 | 3 | Ensure all tasks align with overall business strategy and budget.
Estimated Number of Professionals Involved
ROLE | ESTIMATED INVOLVEMENT | NO. OF PERSON INVOLVE IN THE ROLE
IT Specialist | Full Time | 1
Software Engineer | Full Time | 1
Operations Manager | Full Time | 1
Network Engineer | Full Time | 1
System Administrator | Full Time | 1
Training Specialist | Full Time | 1
Quality Assurance (QA) Manager | Full Time | 1
Business Analyst | Full Time | 1
IT Infrastructure Components( Monitor,Software etc) | 1000000

## sprint8
Sprint 8 Backlog (Weeks 15-16)
Sprint Goal: Staff Training and Trial Run
Task | Description | Assignee | Status | Priority | Comments
Hire Skilled Personnel (Operators, Engineers, Maintenance Staff) | Recruit and onboard skilled personnel | HR Manager | Completed | High | Ensure all key roles are filled with qualified personnel
Develop and Implement Training Programs | Conduct training sessions for staff | Training Manager | Completed | High | Ensure staff is well-prepared for their roles
Conduct Safety Training and Certification | Ensure all staff are safety certified | Safety Officer | Completed | High | Ensure all staff are trained and certified in safety protocols
Develop Quality Assurance Processes and Protocols | Set up quality assurance processes and protocols | Quality Assurance Specialists | Completed | Medium | Ensure quality assurance processes are in place
Conduct Trial Runs and Performance Testing of CNC Machines | Perform trial runs and performance testing of CNC machines | Production Engineers | Completed | Medium | Ensure machines meet performance specifications
Oversee Quality Control During Production | Monitor the quality of products during production. Conduct inspections, record data, and ensure products meet quality standards. | Quality Assurance Specialists | Completed | Medium | Ensure consistent product quality during production.
Operate CNC Machines | Operate CNC machines, perform necessary tasks, and ensure machines function properly during production. | Operators | Completed | High | Ensure smooth operation of CNC machines during production.
Support Mechanical Aspects of Production | Provide technical support for mechanical components, ensure mechanical integrity, and troubleshoot any mechanical issues. | Mechanical Engineers | Completed | Medium | Ensure mechanical components are functioning properly during production.
Professionals Involved | Salaries (per year) |  | Estimated Number of Professionals Involved & their SALARIES
HR Manager | 350000
Training Manager | 587000 |  | ROLE | ESTIMATED INVOLVEMENT | NO. OF PERSON INVOLVE IN THE ROLE | SALARY ALLOCATION (PER WEEK) | TOTAL(week1 + week 2)
Safety Officer | 600000 |  | HR Manager | Full Time | 1 | 7291.67 | 14583.34
Quality Assurance Specialists | 700000 |  | Training Manager | Full Time | 1 | 12229.17 | 24458.34
Production Engineers | 700000 |  | Safety Officer | Full Time | 1 | 12500 | 25000 | Row Labels | Sum of TOTAL(week1 + week 2)
Quality Control Manager | 800000 |  | QA Manager | Full Time | 1 | 14583.34 | 29166.68 | HR Manager | 14583.34
Operators | 350000 |  | Production Engineer | Full Time | 1 | 14583.34 | 29166.68 | 1 | 14583.34
Mechanical Engineer | 800000 |  | Quality Control Manager | Full Time | 1 | 16666.67 | 33333.34 | Full Time | 14583.34
|  |  | Operators | Full Time | 4 | 29166.67 | 58333.34 | Mechanical Engineer | 33333.34
|  |  | Mechanical Engineer | Full Time | 1 | 16666.67 | 33333.34 | 1 | 33333.34
[6 empty] | Total | 247375.06 | Full Time | 33333.34
[8 empty] | Operators | 58333.34
BUDGET ALLOCATED | 300000 | [6 empty] | 4 | 58333.34
MONEY SPEND( salaries + miscellaneous) | 297375.06 | [6 empty] | Full Time | 58333.34
REMAINING | 2624.94 | [6 empty] | Production Engineer | 29166.68
[8 empty] | 1 | 29166.68
[8 empty] | Full Time | 29166.68
Observation: Sprint planning is well within the allocated budget and completed on decided time period. | [7 empty] | QA Manager | 29166.68
[8 empty] | 1 | 29166.68
[8 empty] | Full Time | 29166.68
[8 empty] | Quality Control Manager | 33333.34
[8 empty] | 1 | 33333.34
[8 empty] | Full Time | 33333.34
[8 empty] | Safety Officer | 25000
[8 empty] | 1 | 25000
[8 empty] | Full Time | 25000
[8 empty] | Training Manager | 24458.34
[8 empty] | 1 | 24458.34
[8 empty] | Full Time | 24458.34
[8 empty] | Grand Total | 247375.06

## Cost_Breakdown
COST BREAKDOWN ANALYSIS
Parameters | Cost
Salaries for project Initiation | 100833.34
Salaries for Market Research and Requirement Analysis | 146665.34
Salaries for Engineers & Designers | 279166.04
Utility planning | 212500.04 | Conclusion: The project is well within the allocated budget, with a remaining amount of ₹1,94,836. Each sprint is designed to ensure efficient and effective completion of tasks, with clear roles and responsibilities assigned to professionals. The collaborative approach and adherence to standards will help achieve the project goals, resulting in the successful setup and launch of the CNC machine factory.
Procurement of CNC machine | 7000000
Construction Material Cost | 5000000
Salaries of Estimated number of professionals involved in infrastructure setup | 579166.74
Salaries for professionals involved in CNC Machine Procurement | 7537500.1
IT hardware and software | 651956.36
Staff Training and Trial Run cost | 297375.06
Miscellaneous | 150000
TOTAL | 21955163.02
Budget Allocated | 22500000
Total Estimated Cost | 21955163.02
Remaining Amount | 544836.98